Design C — Learned Sinkhorn for SuperGlue on LEO-NG

Design C Experimental Plan

Learned Unrolled Sinkhorn for SuperGlue on LEO-NG

Target: FP8 E4M3 inference deployment  |  Replaces the 100-iteration log-domain Sinkhorn assignment head

## Plan parameters (as decided)

| Parameter | Value |
| --- | --- |
| Initial iteration count T | 3, with ablation across T ∈ {2, 3, 4, 5, 6} |
| MLP inputs | Scalar summaries + descriptor features (projected from 256 to 8 channels) |
| Deployment mode | Inference-only on LEO-NG FP8 E4M3 PIM accelerator |
| Differentiability | Required during training; not required at inference |
| Timeline | 14 weeks, 6 phases |
| Compute budget | ≈ 350 GPU-hours on A100 or equivalent |

# 1. Objective and success metric

Train a learned assignment head that replaces the 100-iteration log-domain Sinkhorn in SuperGlue’s matcher, unrolled to T = 3 steps with descriptor-conditioned MLP updates. The head must meet all three criteria below on both MegaDepth-1500 and ScanNet-1500 benchmarks.

| Axis | Target | Pass criterion |
| --- | --- | --- |
| Accuracy | Within 1.0 AUC@5° of full SuperGlue Sinkhorn baseline | Measured on held-out benchmark splits |
| Latency | At least 10× reduction in assignment-head wall-clock vs 100-iter Sinkhorn | Measured in the FeatureMatching adapter inference path |
| Precision | Stable in BF16 activation + FP8 E4M3 weight regime | Max marginal error at final iteration < 0.05 across 95% of test pairs |

If all three pass, promote the op to LEO-NG compliance. If any fails, the kill criteria in Section 8 apply.

# 2. Architectural specification

## 2.1 Op registration

A new op, ObservedLearnedSinkhorn, is registered in src/ops/observed_ops.py alongside the existing ObservedSinkhorn. The compliance status is set to “BF16 required” rather than “FP32 required,” reflecting the reduced precision demands from cutting iterations from 100 to 3.

## 2.2 Inputs

- Score matrix S ∈ ℝ^{(M+1)×(N+1)}, including the dustbin row and column, produced by the existing SuperGlue-style GNN.

- SuperPoint descriptors d^A ∈ ℝ^{D×M} and d^B ∈ ℝ^{D×N} with D = 256.

- Dustbin scalar α, learned, identical to current SuperGlue.

## 2.3 Feature construction per row (symmetric for columns)

At each iteration t ∈ {1, ..., T}, a feature vector is assembled for each row i and fed into a shared MLP. All features are derived entirely from the current log transport plan log_T via logsumexp and torch.topk. No exp(), softmax(), or log() is computed in the feature path.

| Feature | Dim | Rationale |
| --- | --- | --- |
| LSE residual: LSE(log_T, row i) | 1 | Log-domain marginal error; the quantity Sinkhorn drives to zero; computed via logsumexp — no exp required |
| Current offset u_i^{(t-1)} | 1 | Cumulative correction so far, prevents overshooting |
| Top-5 gap from row max | 5 | max(log_T, row i) − top-5 values via torch.topk; fully log-domain, no exp required |
| Log-space spread: LSE(log_T, row i) − max(log_T, row i) | 1 | Log-domain sharpness proxy; zero when peaked, grows with flatness; replaces entropy of softmax — no exp or softmax required |
| Descriptor projection Wd_i^A | 8 | Learned linear 256 → 8, gives the update access to content |
| Total input dim | 16 | Per row; symmetric for columns |

## 2.4 MLP architecture

- 3 layers, hidden dim 64, GELU activation, LayerNorm between layers.

- Output dim 1 (scalar Δu_i or Δv_j).

- Weights shared across all T iterations (weight-tied unrolling).

- Two MLPs total: row MLP f_θ and column MLP g_φ.

- Zero-init on the output layer, so at t = 0 the learned update equals 0 and the block reduces to hand-coded Sinkhorn at T = 3. This is critical for the Phase 1 smoke test.

Parameter count: approximately 3,500 total across both MLPs and the descriptor projection. Negligible against the existing ~12 M parameter GNN.

## 2.5 Update rule

log_T is initialized before the loop from S and maintained as the running state. It is passed directly into build_features at every iteration. No exp(), log(), or softmax() is computed anywhere in the feature path; all features are derived from log_T via logsumexp and torch.topk, which operate entirely in log space.

log_T = S.clone()                          # (B, M+1, N+1)

u     = torch.zeros(B, M + 1)             # row log-space offsets

v     = torch.zeros(B, N + 1)             # col log-space offsets

for t in range(T):

# row step — features derived from current log_T, no exp/softmax

features_row = build_features(log_T, u, desc_proj_A, axis='row')

delta_u      = row_mlp(features_row).squeeze(-1)   # (B, M+1)

u            = u + delta_u

# col step — symmetric

features_col = build_features(log_T, v, desc_proj_B, axis='col')

delta_v      = col_mlp(features_col).squeeze(-1)   # (B, N+1)

v            = v + delta_v

# update running log transport plan in log space

log_T = S + u[:, :, None] + v[:, None, :] - norm  # (B, M+1, N+1)

return log_T   # caller applies exp() in FP16 for match extraction only

# 3. Precision plan for LEO-NG

The core argument of Design C is that cutting iterations from 100 to 3 reduces cumulative numerical error by approximately 33×, which in turn relaxes the precision requirement from FP32 to BF16 on the LSE paths. The MLP itself is matmul-heavy and fits natively into FP8 E4M3. The feature path (build_features) is entirely log-domain and requires no exp or softmax.

| Component | Precision | Rationale |
| --- | --- | --- |
| GNN body (existing) | FP8 E4M3 | Matches existing quantize_components: ["superglue"] config |
| Score matmul S = Dᵀ D’ | FP8 E4M3 | Standard matmul, handled by existing QuantMatMul |
| log T = S + u + v | FP16 | Addition of small log-space values; FP8 dynamic range insufficient |
| LSE per iteration (T=3 only) | BF16 | Cumulative error ~33× smaller than T=100; BF16 sufficient |
| build_features (logsumexp, topk) | BF16 | Entirely log-domain; no exp or softmax in the feature path |
| Row/col MLP weights | FP8 E4M3 per-channel | Small weights, per-channel quantization preserves accuracy |
| Row/col MLP activations | FP16 | Activation precision dominates accuracy for small MLPs |
| Final exp for match extraction | FP16 | One-shot operation outside the loop, not iterated |

# 4. Loss function and training objective

Three loss terms are combined to balance matching accuracy, iteration-wise convergence, and preservation of the marginal-constraint property that makes Sinkhorn useful.

ℒ = ℒmatch + λmarg · ℒmarg + λaux · ℒaux

### 4.1 Matching loss (primary)

Negative log-likelihood of the final log transport plan at ground-truth match positions and at dustbin positions, identical to the SuperGlue paper’s loss formulation.

### 4.2 Marginal regularizer

L2 penalty on deviation of final row and column sums from the target marginals.

- Initial weight λ_marg = 0.1

- Annealed to 0.01 after epoch 10

### 4.3 Auxiliary intermediate-iteration loss

Primary matching loss applied at intermediate iterations t = 1 and t = 2, weighted 0.3 each. Provides extra gradient signal and prevents the network from delaying convergence to only the final iteration.

# 5. Phased execution plan

## 5.1 Timeline summary

| Phase | Duration | Deliverable |
| --- | --- | --- |
| 0 | Week 1 | Baseline table reproducing SuperGlue paper numbers within ±0.5 AUC@5° |
| 1 | Weeks 2–3 | ObservedLearnedSinkhorn op + unit tests + adapter integration |
| 2 | Weeks 4–6 | Head-only training (GNN frozen), best checkpoint on ScanNet val |
| 3 | Week 7 | Ablation over T ∈ {2, 3, 4, 5, 6}, chosen T* |
| 4 | Weeks 8–10 | Joint GNN + head fine-tuning, full benchmark evaluation |
| 5 | Weeks 11–13 | FP8 quantization and LEO-NG precision sensitivity analysis |
| 6 | Week 14 | Final comparison, decision memo, go/no-go recommendation |

# 6. Risk register

| Risk | Signal | Mitigation |
| --- | --- | --- |
| R1 — MLPs learn to ignore inputs and reproduce plain Sinkhorn | KL divergence between learned and hand-coded T=3 Sinkhorn stays < 0.1 throughout training | Zero-init output layer so the network starts at Sinkhorn and must actively diverge. Monitor MLP output norm and KL metric every 2 epochs. |
| R2 — Unrolled block is unstable to train | Gradient norms explode; loss diverges; NaN in u or v | Gradient clipping at 1.0; LayerNorm inside MLP; auxiliary loss at intermediate iterations provides extra gradient signal. |
| R3 — Accuracy does not beat dual-softmax + matchability baseline | Phase 4 final AUC is more than 0.5 points below a LightGlue reference run with same SuperPoint frontend | Hard kill criterion at end of Phase 2. Pivot to LightGlue port. |

# 7. Consolidated kill criteria

| Phase | Condition | Action |
| --- | --- | --- |
| 0 | Harness cannot reproduce SuperGlue paper numbers within 0.5 AUC@5° | Fix harness first, no pivot yet |
| 1 | Op at zero-init does not match hand-coded T=3 Sinkhorn | Fix op implementation, no pivot yet |
| 2 | Learned T=3 does not beat hand-coded T=3 by 0.5 AUC@5° | Kill Design C, pivot to LightGlue |
| 2 | MLPs have not meaningfully diverged from hand-coded Sinkhorn (KL < 0.1) | Kill: learned updates not earning capacity |
| 3 | Best T exceeds 5 | Kill: Design C not cheaper than Sinkhorn in practice |
| 4 | Cannot come within 1.0 AUC@5° of full SuperGlue on both benchmarks | Kill: accuracy ceiling too low |
| 5 | No precision config keeps quantization cost under 2.0 AUC@5° vs FP32 | Kill: not FP8-deployable |

# 8. Resource envelope

| Resource | Requirement |
| --- | --- |
| Engineering | 1 engineer full-time for 14 weeks, or 2 engineers for 8 weeks with Phase 2 and Phase 3 parallelized |
| Compute (Phases 0–1) | 1 × A100 or equivalent |
| Compute (Phases 2–5) | 2 × A100, with Phase 3 ablation parallelized across the two |
| GPU-hours | Approximately 350 GPU-hours total |
| Data | ScanNet (approx. 1 TB); MegaDepth-1500 test set (~5 GB) |
| Risk-adjusted shipping probability | 30–40% based on kill gates. Most similar projects fail at Phase 2 gate 3 or Phase 4. |

# 9. File and experiment layout

design_c/

baselines.csv

configs/

learned_sinkhorn_p2.yaml

learned_sinkhorn_p4.yaml

learned_sinkhorn_p5_fp8.yaml

checkpoints/

p2_head_only_best.pt

p4_joint_best.pt

p5_quantized.pt

ablation_T/

t2.csv, t3.csv, t4.csv, t5.csv, t6.csv

summary.csv

results/

final_comparison.csv

precision_sensitivity.csv

decision_memo.md

# 10. Key references

- P.-E. Sarlin et al., “SuperGlue: Learning Feature Matching with Graph Neural Networks,” Proc. IEEE/CVF CVPR, pp. 4938–4947, 2020.

- M. Cuturi, “Sinkhorn Distances: Lightspeed Computation of Optimal Transport Distances,” Proc. NeurIPS, vol. 26, 2013.

- P. Lindenberger, P.-E. Sarlin, M. Pollefeys, “LightGlue: Local Feature Matching at Light Speed,” Proc. ICCV, 2023 (fallback path reference).

- K. Gregor, Y. LeCun, “Learning Fast Approximations of Sparse Coding,” Proc. ICML, 2010 (foundational work on unrolled optimization).

- M. Eisenberger et al., “A Unified Framework for Implicit Sinkhorn Differentiation,” Proc. CVPR, 2022.

- M. E. Sander et al., “Sinkformers: Transformers with Doubly Stochastic Attention,” Proc. AISTATS, 2022.